## Sheet1
Project Cost Estimate
| # of Units/Hrs | Cost/Unit or hr | SubTotals | WBS level 2 Totals | % of Total
WBS Items
1. Project Management
1.1 Initiation
1.1.1. Identify Stakeholders | 7.5
1.1.2 Develop Project Charter | 15
1.1.3 Hold a kick-off meeting | 20
1.2 Planning
1.2.1 Collect Requirements | 30
1.2.2 Plan scope management | 22.5
1.2.3 Develop Scope Statement | 15
1.2.4 Create WBS | 22.5
1.2.5 Define activities | 15
1.2.6 Sequence activities | 15
1.2.7 Estimate activity duration | 22.5
1.2.8 Develop Schedule Management Plan | 90
1.2.9 Develop a schedule | 45
1.2.10 Develop a quality management plan | 30
1.2.11 Develop a resource management plan | 60
1.2.12 Plan cost management | 45
1.2.13 Estimate costs | 7.5
1.2.14 Determine budget | 33
1.2.15 Plan risk management | 45
1.3 Execution
1.3.1 Define the required parts of the robot | 135
1.3.2 Design a model of Robot | 157.5
1.3.3 Multiple Agricultural Tasks
1.3.3.1 Gather information from R&D team | 14
1.3.3.2 Identify tasks | 84
1.3.3.3 Develop algorithms for each task
1.3.3.3.1 Develop AI Perception Algorithm | 225
1.3.3.3.2 Build Vision Algorithms | 300
1.3.3.3.3 Create Maneuver Algorithms | 225
1.3.3.3.4 Develop Balancing Algorithms | 300
1.3.3.3.5 Build Harvesting Optimization System | 300
1.3.3.4 Build database tables and schemas | 90
1.3.3.5 Create Data Structures, Functions and Iterative loops | 168
1.3.3.6 Develop storage for tracking records | 135
1.3.3.7 Build security system for records | 60
1.3.4 Picking multiple variety fruits
1.3.4.1 Create a list of fruits | 22
1.3.4.2 Gather details of fruits | 24
1.3.4.3 Create an algorithm for picking process | 148
1.3.4.4 Implement algorithm for harvesting fruits | 53
1.3.4.5 Develop a system for real-time recording of fruits | 108
1.3.4.6 Create database tables and schemas for harvesting records | 57
1.3.4.7 Develop a user interface to show fruit-picking records | 135
1.3.5 Multi Orchard Design
1.3.5.1 Gather data on types of orchard designs available from the R&D team | 7.5
1.3.5.2 Assess available area and accommodate number of orchards | 22.5
1.3.5.3 Develop an algorithm for finding the similar cultivation process | 210
1.3.5.4 Implement best orchard layout which maximizes yield and quality | 100
1.3.5.5 Develop a security algorithm for encrypting an algorithms data | 90
1.3.6 Multi-platform access
1.3.6.1 Build wireframes for the interface of an application | 54
1.3.6.2 Develop Mock-ups | 52
1.3.6.3 Create a schema for the database | 42
1.3.6.4 Develop front-end from Mock-ups | 105
1.3.6.5 Build backend with data analytics | 260
1.3.6.6 Deploy the app to the cloud platform | 12
1.3.7 Implement algorithms to the robot's model | 300
1.3.8 Test the product | 63
1.4 Monitoring & Controlling
1.4.1 View all generated logs | 350
1.4.2 Identify potential issues with an algorithm | 800
1.4.3 Monitor the process and accuracy of the algorithm | 800
1.4.4 Monitor the performance of an algorithm | 800
1.4.5 Integrate changes | 445
1.4.6 Maintain security standards | 1496
1.4.7 Correct the documentation according to the integreted changes | 350
1.4.8 All issues were solved and Documented | 350
1.5 Closing
1.5.1 Close project | 27
2.Hardware
Handheld Devices | 20 | 1200 | 24000
Robotics Material |  |  | 30000
Cloud Server | 6 | 2000 | 12000
Internet | 3 | 150 | 450
3. Software
License software | 12 | 250 | 3000
Software Development (Exec) |  |  | 193465.7
4.Testing(10% of Total Hardware and Software cost)
5.Training and Support
Trainee cost | 100 | 250 | 25000
Travel Cost | 374 | 15 | 5610
Project Team Member |  |  | 0
Subtotal |  |  | 293525.7
6. Reserves (20% of Total Estimate)
Total Project Cost Estimate